|  | Event Date/ Deadline | Task | Notes |
| --- | --- | --- | --- |
|  | 3/11/2024 | Deadline: Post ELECT's June order calling primary notice either on the county's/city's website, at least 10 public places, or have notice published at least once in a newspaper of general circulation. |  |
|  | 4/4/2024 | End: Candidate filing deadline |  |
|  | 4/5/2024 | Reminder: GR to confirm 1) all candidate filings have been submitted, reviewed, are complete and accurate, and have been processed, and 2) all candidate records in VERIS have been set up and are complete and accurate. Note: Ensuring VERIS is completely up to date satisfies the reporting requirements in § 24.2-505 & 24.2-612 (Candidate lists to ELECT). |  |
|  | 4/9/2024 | End: Party filing deadline |  |
|  | 4/10/2024 | Reminder: GR to confirm 1) all party filings have been submitted, reviewed, are complete and accurate, and have been processed, 2) all candidate records in VERIS have been updated and are complete and accurate, and 3) unopposed candidate records are copied over to the November election in VERIS. Reminder: Ensuring VERIS is completely up to date satisfies the reporting requirements in § 24.2-505 & 24.2-612 (Candidate lists to ELECT). |  |
|  | 4/12/2024 | Start: General registrars begin submitting ballot proofs to ELECT for review and approval. |  |
|  | 4/19/2024 | Deadline: EB to send notice to treasurer/director of finance to return primary filing fees for unopposed, disqualified, or withdrawn primary candidates who withdrew before the Party Chair certified the nominee(s). |  |
|  | 4/19/2024 | Survey Due: Locality Use of Satellite Locations and Drop Boxes Survey (includes Satellite Readiness Checklist) |  |
|  | 4/19/2024 | Survey Due: Locality Use of Ballot on Demand Printers for 6/18/24 Primaries |  |
|  | 4/20/2024 | Reminder: Absentee voting equipment custodian(s) must be appointed prior to testing absentee voting equipment. |  |
|  | 4/24/2024 | Deadline: Post notice of early voting and satellite locations |  |
|  | 4/24/2024 | Survey Due: Ballots Being Ordered Survey |  |
|  | 4/24/2024 | Start: Enhanced Ballot ready for set up and emailing UOCAVA and print disabled ballots. (This is a goal. ELECT will notify localities once Enhanced Ballot is ready.) |  |
|  | 4/24/2024 | Start: Enhanced Results ready for verification and testing. (This is a goal. ELECT will notify localities once Enhanced Results is ready.) |  |
|  | 5/2/2024 | Deadline: Last day for L&A voting systems and EPB testing before absentee voting. Absentee voting equipment custodian(s) must be appointed prior to testing absentee voting equipment. |  |
|  | 5/2/2024 | Survey Due: Must certify L&A testing for voting machines and EPBs to ELECT. |  |
|  | 5/3/2024 | Start: Absentee and Early Voting |  |
|  | 5/3/2024 | Survey Due: AB Compliance Survey |  |
|  | 5/10/2024 | Survey Due: Election Setup Verification Survey (VERIS and ENR) |  |
|  | 5/17/2024 | Deadline: GR to give notice of date, hours, and locations for final day of voter registration. |  |
|  | 5/19/2024 | Reminder: New officers of election and officers starting a new term must receive training before the first election in which they will be serving. EBs must certify to ELECT all the newly trained officers. |  |
|  | 5/19/2024 | Deadline: Election Day voting equipment custodian(s) must be appointed prior to testing election day voting equipment. |  |
|  | 5/19/2024 | Start: First day local electoral boards can train Chief and Deputy Chief officers of election. |  |
|  | 5/27/2024 | Holiday: Memorial Day |  |
|  | 5/28/2024 | End: Last day for voter registration |  |
|  | 5/29/2024 | Start: Same Day Voter Registration begins for June Primaries |  |
|  | 6/7/2024 | End: Last day to apply via online, fax, or mail for an absentee ballot. |  |
|  | 6/8/2024 | Saturday Open: GR's office open a minimum of eight hours between 8 am - 5 pm for in-person absentee voting. |  |
|  | 6/11/2024 | Deadline: Mandatory pre-processing of absentee ballots. The pre-processing of absentee ballots is mandatory for general registrars’ offices “beginning on the seventh day immediately preceding the election”. |  |
|  | 6/15/2024 | Saturday Open: GR's office open a minimum of eight hours between 8 am - 5 pm for in-person absentee voting. Last day of early voting and early SDR. |  |
|  | 6/15/2024 | End: Last day of early voting and early SDR. |  |
|  | 6/15/2024 | Deadline: 2nd round mandatory pre-processing of absentee ballots. This second round of pre-processing can be done on Friday (6/14/24) or Saturday (6/15/24). |  |
|  | 6/15/2024 | Deadline: Last day for local electoral boards to train Chief and Deputy Chief officers of election. |  |
|  | 6/17/2024 | Deadline: Last day testing of Election Day voting systems and EPBs can be done prior to election day. |  |
|  | 6/17/2024 | Survey Due: Must certify L&A testing for voting machines and EPBs to ELECT. |  |
|  | 6/17/2024 | End: Last day a voter can request an emergency absentee ballot. (Certain restrictions apply.) |  |
|  | 6/18/2024 | PRIMARY ELECTION DAY |  |
|  | 6/19/2024 | Holiday: Juneteenth |  |
|  | 6/20/2024 | Start: Local election results certification (provisional ballot meeting and canvass). |  |
|  | 6/22/2024 | Reminder: Review SDR Duplicate Report (will be emailed to general registrars from ELECT's Elections Admin team) |  |
|  | 6/24/2024 | Deadline: Abstracts of Votes must be submitted electronically to ELECT via the Abstract of Votes Submission Formsite form. Originals are not to be mailed until Formsite submissions are approved. |  |
|  | 6/25/2024 | Deadline: Ballot on Demand Localities need to submit summary and attestation documents electronically to ELECT via the BOD Election Summary Documentation Formsite form. |  |