|  | Event Date/ Deadline | Task | Notes |
| --- | --- | --- | --- |
|  | 1/5/2024 | Survey Due: Locality Use of Satellite Locations and Drop Boxes Survey (includes Satellite Readiness Checklist) |  |
|  | 1/5/2024 | Survey Due: Locality Use of Ballot on Demand Printers for 3/5/24, Presidential Primaries |  |
|  | 1/6/2024 | Reminder: Absentee voting equipment custodian(s) must be appointed prior to testing absentee voting equipment. |  |
|  | 1/10/2024 | Deadline: Post notice of early voting and satellite locations |  |
|  | 1/10/2024 | Survey Due: Ballots Being Ordered Survey |  |
|  | 1/15/2034 | Holiday: MLK Jr Day |  |
|  | 1/18/2024 | Deadline: Last day for L&A voting systems and EPB testing before absentee voting. Absentee voting equipment custodian(s) must be appointed prior to testing absentee voting equipment. |  |
|  | 1/18/2024 | Survey Due: Must certify L&A testing for voting machines and EPBs to ELECT. |  |
|  | 1/19/2024 | Start: Absentee and Early Voting |  |
|  | 1/19/2024 | Survey Due: AB Compliance Survey Due |  |
|  | 1/26/2024 | Survey Due: Election Setup Verification Survey (VERIS and ENR) |  |
|  | 2/2/2024 | Deadline: GR to give notice of date, hours, and locations for final day of voter registration. |  |
|  | 2/4/2024 | Reminder: New officers of election and officers starting a new term must receive training before the first election in which they will be serving. EBs must certify to ELECT all the newly trained officers. |  |
|  | 2/4/2024 | Deadline: Election Day voting equipment custodian(s) must be appointed prior to testing election day voting equipment. |  |
|  | 2/4/2024 | Start: First day local electoral boards can train Chief and Deputy Chief officers of election. |  |
|  | 2/12/2024 | End: Last day for voter registration |  |
|  | 2/13/2024 | Start: Same Day Voter Registration begins for March presidential primary. |  |
|  | 2/19/2024 | Holiday: George Washington Day |  |
|  | 2/23/2024 | End: Last day to apply via online, fax, or mail for an absentee ballot. |  |
|  | 2/24/2024 | Saturday Open: GR's office open a minimum of eight hours between 8 am - 5 pm for in-person absentee voting. |  |
|  | 2/27/2024 | Deadline: Mandatory pre-processing of absentee ballots. The pre-processing of absentee ballots is mandatory for general registrars’ offices “beginning on the seventh day immediately preceding the election”. |  |
|  | 3/2/2024 | Saturday Open: GR's office open a minimum of eight hours between 8 am - 5 pm for in-person absentee voting. |  |
|  | 3/2/2024 | End: Last day of early voting and early SDR. |  |
|  | 3/2/2024 | Deadline: 2nd round mandatory pre-processing of absentee ballots. This second round of pre-processing can be done on Friday (3/1/24) or Saturday (3/2/24). |  |
|  | 3/2/2024 | Deadline: Last day for local electoral boards to train Chief and Deputy Chief officers of election. |  |
|  | 3/4/2024 | Deadline: Last day testing of Election Day voting systems and EPBs can be done prior to election day. |  |
|  | 3/4/2024 | Survey Due: Must certify L&A testing for voting machines and EPBs to ELECT. |  |
|  | 3/4/2024 | End: Last day a voter can request an emergency absentee ballot. (Certain restrictions apply.) |  |
|  | 3/5/2024 | PRIMARY ELECTION DAY |  |
|  | 3/6/2024 | Start: Local election results certification (provisional ballot meeting and canvass). |  |
|  | 3/9/2024 | Reminder: Review SDR Duplicate Report (will be emailed to general registrars from ELECT's Elections Admin team) |  |
|  | 3/11/2024 | Deadline: Abstracts of Votes must be submitted electronically to ELECT via the Abstract of Votes Submission Formsite form. Originals are not to be mailed until Formsite submissions are approved. |  |
|  | 3/12/2024 | Deadline: Ballot on Demand Localities need to submit summary and attestation documents electronically to ELECT via the BOD Election Summary Documentation Formsite form. |  |